## Schedule
WBS | Task | Duration (working days) | Start | Finish | Predecessors | Responsible | Total float (days) | Critical
1.0 | Project management |  | 2027-02-01 | 2028-01-28
1.1.1 | Develop project charter | 10 | 2027-02-01 | 2027-02-12 | — | Arjun Mehta | 0 | Yes
1.1.2 | Charter review and sponsor sign-off | 5 | 2027-02-15 | 2027-02-19 | 1.1.1 | Helen Fraser | 0 | Yes
M1 | Project charter approved | 0 | 2027-02-19 | 2027-02-19 | 1.1.2 | Helen Fraser | 0 | Yes
1.2.1 | Project management plan and baselines | 15 | 2027-02-22 | 2027-03-15 | M1 | Arjun Mehta | 45
1.3.1 | Risk, quality and communication plans | 10 | 2027-02-22 | 2027-03-05 | M1 | Arjun Mehta | 50
1.4.1 | Monitoring, control and reporting | Ongoing | 2027-02-22 | 2028-01-28 | — | Arjun Mehta
2.0 | Discovery and assessment |  | 2027-02-22 | 2027-04-07
2.1.1 | Application and infrastructure inventory | 10 | 2027-02-22 | 2027-03-05 | M1 | Mei Ling Tan | 0 | Yes
2.2.1 | Map dependencies between systems | 10 | 2027-03-09 | 2027-03-22 | 2.1.1 | Sarah Kim | 0 | Yes
2.3.1 | Select 7R strategies and wave plan | 5 | 2027-03-23 | 2027-03-31 | 2.2.1 | Sarah Kim | 0 | Yes
2.4.1 | Validate business case and budget | 5 | 2027-04-01 | 2027-04-07 | 2.3.1 | Arjun Mehta | 30
3.0 | Cloud foundation (AWS landing zone) |  | 2027-04-01 | 2027-05-19
3.1.1 | Design AWS landing zone | 10 | 2027-04-01 | 2027-04-14 | 2.3.1 | Sarah Kim | 0 | Yes
3.2.1 | Network connectivity to AWS | 15 | 2027-04-15 | 2027-05-05 | 3.1.1 | Lucas Silva | 5
3.3.1 | Identity and access management | 10 | 2027-04-15 | 2027-04-28 | 3.1.1 | Thomas Walker | 0 | Yes
3.4.1 | Security controls, logging, monitoring | 10 | 2027-04-29 | 2027-05-12 | 3.3.1 | Thomas Walker | 0 | Yes
3.5.1 | Landing zone review and sign-off | 5 | 2027-05-13 | 2027-05-19 | 3.2.1, 3.4.1 | Thomas Walker | 0 | Yes
M2 | AWS landing zone ready | 0 | 2027-05-19 | 2027-05-19 | 3.5.1 | Sarah Kim | 0 | Yes
4.0 | Migration Wave 1 |  | 2027-05-20 | 2027-08-03
4.1.1 | Wave 1 migration design | 5 | 2027-05-20 | 2027-05-26 | M2, 1.2.1, 1.3.1, 2.4.1 | Sarah Kim | 0 | Yes
4.2.1 | Configure SaaS payroll and rehost DMS | 15 | 2027-05-27 | 2027-06-17 | 4.1.1 | AWS partner team | 0 | Yes
4.3.1 | Wave 1 data migration trial | 5 | 2027-06-18 | 2027-06-24 | 4.2.1 | Mei Ling Tan | 0 | Yes
4.4.1 | Wave 1 functional/integration testing | 10 | 2027-06-25 | 2027-07-08 | 4.3.1 | Olivia Brown | 0 | Yes
4.4.2 | Wave 1 security testing | 5 | 2027-06-18 | 2027-06-24 | 4.2.1 | Thomas Walker | 10
4.4.3 | Wave 1 user acceptance testing | 5 | 2027-07-09 | 2027-07-15 | 4.4.1, 4.4.2 | Olivia Brown | 0 | Yes
4.5.1 | Wave 1 go/no-go and cutover | 1 | 2027-07-16 | 2027-07-16 | 4.4.3, 8.3.1, 7.2.1 | Arjun Mehta | 0 | Yes
M3 | Wave 1 live | 0 | 2027-07-16 | 2027-07-16 | 4.5.1 | Arjun Mehta | 0 | Yes
4.6.1 | Wave 1 hypercare support | 10 | 2027-07-19 | 2027-07-30 | M3 | Sarah Kim | 0 | Yes
4.6.2 | Wave 1 lessons learned | 2 | 2027-08-02 | 2027-08-03 | 4.6.1 | Arjun Mehta | 0 | Yes
5.0 | Migration Wave 2 |  | 2027-05-27 | 2027-10-11
5.1.1 | Wave 2 migration design | 10 | 2027-05-27 | 2027-06-09 | 4.1.1 | Sarah Kim | 18
5.2.1 | Build CRM and data warehouse on AWS | 20 | 2027-06-10 | 2027-07-08 | 5.1.1 | AWS partner team | 18
5.3.1 | Wave 2 data migration trials | 10 | 2027-08-04 | 2027-08-17 | 5.2.1, 4.6.2 | Mei Ling Tan | 0 | Yes
5.4.1 | Wave 2 functional/integration testing | 15 | 2027-08-18 | 2027-09-07 | 5.3.1 | Olivia Brown | 0 | Yes
5.4.2 | Wave 2 security testing | 5 | 2027-07-09 | 2027-07-15 | 5.2.1 | Thomas Walker | 38
5.4.3 | Wave 2 performance testing | 5 | 2027-08-18 | 2027-08-24 | 5.3.1 | Olivia Brown | 10
5.4.4 | Wave 2 user acceptance testing | 7 | 2027-09-08 | 2027-09-16 | 5.4.1, 5.4.2, 5.4.3 | Olivia Brown | 0 | Yes
5.5.1 | Wave 2 go/no-go and cutover | 1 | 2027-09-17 | 2027-09-17 | 5.4.4, 8.3.2 | Arjun Mehta | 0 | Yes
M4 | Wave 2 live | 0 | 2027-09-17 | 2027-09-17 | 5.5.1 | Arjun Mehta | 0 | Yes
5.6.1 | Wave 2 hypercare support | 10 | 2027-09-20 | 2027-10-04 | M4 | Sarah Kim | 0 | Yes
5.6.2 | Retire old reporting server | 5 | 2027-10-05 | 2027-10-11 | 5.6.1 | Lucas Silva | 65
5.6.3 | Wave 2 lessons learned | 2 | 2027-10-05 | 2027-10-06 | 5.6.1 | Arjun Mehta | 0 | Yes
6.0 | Migration Wave 3 |  | 2027-06-10 | 2027-12-07
6.1.1 | Wave 3 migration design | 15 | 2027-06-10 | 2027-07-01 | 5.1.1 | Sarah Kim | 18
6.2.1 | Refactor internet banking portal | 50 | 2027-07-02 | 2027-09-09 | 6.1.1 | AWS partner team | 18
6.3.1 | Replatform loan origination system | 25 | 2027-07-02 | 2027-08-05 | 6.1.1 | AWS partner team | 43
6.4.1 | Wave 3 data migration trials | 10 | 2027-10-07 | 2027-10-20 | 6.2.1, 6.3.1, 5.6.3 | Mei Ling Tan | 0 | Yes
6.5.1 | Wave 3 functional/integration testing | 15 | 2027-10-21 | 2027-11-11 | 6.4.1 | Olivia Brown | 0 | Yes
6.5.2 | Wave 3 security and penetration testing | 10 | 2027-09-10 | 2027-09-23 | 6.2.1, 6.3.1 | Thomas Walker | 33
6.5.3 | Wave 3 performance and load testing | 5 | 2027-10-21 | 2027-10-27 | 6.4.1 | Olivia Brown | 10
6.5.4 | Wave 3 user acceptance testing | 5 | 2027-11-12 | 2027-11-18 | 6.5.1, 6.5.2, 6.5.3 | Olivia Brown | 0 | Yes
6.6.1 | Wave 3 go/no-go and cutover | 1 | 2027-11-19 | 2027-11-19 | 6.5.4, 8.3.3, 8.4.1, 7.3.1 | Arjun Mehta | 0 | Yes
M5 | Wave 3 live | 0 | 2027-11-19 | 2027-11-19 | 6.6.1 | Arjun Mehta | 0 | Yes
6.7.1 | Wave 3 hypercare support | 10 | 2027-11-22 | 2027-12-03 | M5 | Sarah Kim | 20
6.7.2 | Wave 3 lessons learned | 2 | 2027-12-06 | 2027-12-07 | 6.7.1 | Arjun Mehta | 20
7.0 | Compliance and security assurance |  | 2027-04-01 | 2027-11-24
7.1.1 | APRA compliance assessment | 10 | 2027-04-01 | 2027-04-14 | 2.3.1 | Thomas Walker | 60
7.2.1 | Regulator notification | 5 | 2027-04-15 | 2027-04-21 | 7.1.1 | Thomas Walker | 60
7.3.1 | Independent security audit | 10 | 2027-07-19 | 2027-07-30 | M3 | Thomas Walker | 77
7.4.1 | Final compliance sign-off | 3 | 2027-11-22 | 2027-11-24 | M5, 7.3.1 | Thomas Walker | 39
8.0 | Training and change management |  | 2027-04-01 | 2027-11-18
8.1.1 | Change impact and training needs | 10 | 2027-04-01 | 2027-04-14 | 2.3.1 | Ahmed Hassan | 45
8.2.1 | Develop training materials | 15 | 2027-04-15 | 2027-05-05 | 8.1.1 | Ahmed Hassan | 45
8.3.1 | Wave 1 staff training | 5 | 2027-07-09 | 2027-07-15 | 8.2.1, 4.4.1 | Ahmed Hassan | 0 | Yes
8.3.2 | Wave 2 staff training | 5 | 2027-09-08 | 2027-09-14 | 5.4.1 | Ahmed Hassan | 2
8.3.3 | Wave 3 staff training | 5 | 2027-11-12 | 2027-11-18 | 6.5.1 | Ahmed Hassan | 0 | Yes
8.4.1 | Customer communications (Wave 3) | 10 | 2027-10-21 | 2027-11-04 | 6.4.1 | Ahmed Hassan | 10
9.0 | Decommission and closure |  | 2027-11-22 | 2028-01-28
9.1.1 | Stability period (to end of freeze) | 32 | 2027-11-22 | 2028-01-07 | M5 | Sarah Kim | 0 | Yes
9.2.1 | Archive legacy data | 5 | 2028-01-10 | 2028-01-14 | 9.1.1, 6.7.2 | Mei Ling Tan | 0 | Yes
9.3.1 | Decommission on-premises servers | 5 | 2028-01-17 | 2028-01-21 | 9.2.1, 5.6.2 | Lucas Silva | 0 | Yes
9.4.1 | Final project report | 3 | 2028-01-24 | 2028-01-27 | 9.3.1, 7.4.1 | Arjun Mehta | 0 | Yes
9.5.1 | Closure and sponsor sign-off | 1 | 2028-01-28 | 2028-01-28 | 9.4.1 | Helen Fraser | 0 | Yes
M6 | Project closed | 0 | 2028-01-28 | 2028-01-28 | 9.5.1 | Helen Fraser | 0 | Yes

## Gantt (weekly)
WBS | Task | Start | Finish | 01 Feb | 08 Feb | 15 Feb | 22 Feb | 01 Mar | 08 Mar | 15 Mar | 22 Mar | 29 Mar | 05 Apr | 12 Apr | 19 Apr | 26 Apr | 03 May | 10 May | 17 May | 24 May | 31 May | 07 Jun | 14 Jun | 21 Jun | 28 Jun | 05 Jul | 12 Jul | 19 Jul | 26 Jul | 02 Aug | 09 Aug | 16 Aug | 23 Aug | 30 Aug | 06 Sep | 13 Sep | 20 Sep | 27 Sep | 04 Oct | 11 Oct | 18 Oct | 25 Oct | 01 Nov | 08 Nov | 15 Nov | 22 Nov | 29 Nov | 06 Dec | 13 Dec | 20 Dec | 27 Dec | 03 Jan | 10 Jan | 17 Jan | 24 Jan | 31 Jan
1.0 | Project management | 2027-02-01 | 2028-01-28
1.1.1 | Develop project charter | 2027-02-01 | 2027-02-12
1.1.2 | Charter review and sponsor sign-off | 2027-02-15 | 2027-02-19
M1 | Project charter approved | 2027-02-19 | 2027-02-19 |  |  | ◆
1.2.1 | Project management plan and baselines | 2027-02-22 | 2027-03-15
1.3.1 | Risk, quality and communication plans | 2027-02-22 | 2027-03-05
1.4.1 | Monitoring, control and reporting | 2027-02-22 | 2028-01-28
2.0 | Discovery and assessment | 2027-02-22 | 2027-04-07
2.1.1 | Application and infrastructure inventory | 2027-02-22 | 2027-03-05
2.2.1 | Map dependencies between systems | 2027-03-09 | 2027-03-22
2.3.1 | Select 7R strategies and wave plan | 2027-03-23 | 2027-03-31
2.4.1 | Validate business case and budget | 2027-04-01 | 2027-04-07
3.0 | Cloud foundation (AWS landing zone) | 2027-04-01 | 2027-05-19
3.1.1 | Design AWS landing zone | 2027-04-01 | 2027-04-14
3.2.1 | Network connectivity to AWS | 2027-04-15 | 2027-05-05
3.3.1 | Identity and access management | 2027-04-15 | 2027-04-28
3.4.1 | Security controls, logging, monitoring | 2027-04-29 | 2027-05-12
3.5.1 | Landing zone review and sign-off | 2027-05-13 | 2027-05-19
M2 | AWS landing zone ready | 2027-05-19 | 2027-05-19 | [15 empty] | ◆
4.0 | Migration Wave 1 | 2027-05-20 | 2027-08-03
4.1.1 | Wave 1 migration design | 2027-05-20 | 2027-05-26
4.2.1 | Configure SaaS payroll and rehost DMS | 2027-05-27 | 2027-06-17
4.3.1 | Wave 1 data migration trial | 2027-06-18 | 2027-06-24
4.4.1 | Wave 1 functional/integration testing | 2027-06-25 | 2027-07-08
4.4.2 | Wave 1 security testing | 2027-06-18 | 2027-06-24
4.4.3 | Wave 1 user acceptance testing | 2027-07-09 | 2027-07-15
4.5.1 | Wave 1 go/no-go and cutover | 2027-07-16 | 2027-07-16
M3 | Wave 1 live | 2027-07-16 | 2027-07-16 | [23 empty] | ◆
4.6.1 | Wave 1 hypercare support | 2027-07-19 | 2027-07-30
4.6.2 | Wave 1 lessons learned | 2027-08-02 | 2027-08-03
5.0 | Migration Wave 2 | 2027-05-27 | 2027-10-11
5.1.1 | Wave 2 migration design | 2027-05-27 | 2027-06-09
5.2.1 | Build CRM and data warehouse on AWS | 2027-06-10 | 2027-07-08
5.3.1 | Wave 2 data migration trials | 2027-08-04 | 2027-08-17
5.4.1 | Wave 2 functional/integration testing | 2027-08-18 | 2027-09-07
5.4.2 | Wave 2 security testing | 2027-07-09 | 2027-07-15
5.4.3 | Wave 2 performance testing | 2027-08-18 | 2027-08-24
5.4.4 | Wave 2 user acceptance testing | 2027-09-08 | 2027-09-16
5.5.1 | Wave 2 go/no-go and cutover | 2027-09-17 | 2027-09-17
M4 | Wave 2 live | 2027-09-17 | 2027-09-17 | [32 empty] | ◆
5.6.1 | Wave 2 hypercare support | 2027-09-20 | 2027-10-04
5.6.2 | Retire old reporting server | 2027-10-05 | 2027-10-11
5.6.3 | Wave 2 lessons learned | 2027-10-05 | 2027-10-06
6.0 | Migration Wave 3 | 2027-06-10 | 2027-12-07
6.1.1 | Wave 3 migration design | 2027-06-10 | 2027-07-01
6.2.1 | Refactor internet banking portal | 2027-07-02 | 2027-09-09
6.3.1 | Replatform loan origination system | 2027-07-02 | 2027-08-05
6.4.1 | Wave 3 data migration trials | 2027-10-07 | 2027-10-20
6.5.1 | Wave 3 functional/integration testing | 2027-10-21 | 2027-11-11
6.5.2 | Wave 3 security and penetration testing | 2027-09-10 | 2027-09-23
6.5.3 | Wave 3 performance and load testing | 2027-10-21 | 2027-10-27
6.5.4 | Wave 3 user acceptance testing | 2027-11-12 | 2027-11-18
6.6.1 | Wave 3 go/no-go and cutover | 2027-11-19 | 2027-11-19
M5 | Wave 3 live | 2027-11-19 | 2027-11-19 | [41 empty] | ◆
6.7.1 | Wave 3 hypercare support | 2027-11-22 | 2027-12-03
6.7.2 | Wave 3 lessons learned | 2027-12-06 | 2027-12-07
7.0 | Compliance and security assurance | 2027-04-01 | 2027-11-24
7.1.1 | APRA compliance assessment | 2027-04-01 | 2027-04-14
7.2.1 | Regulator notification | 2027-04-15 | 2027-04-21
7.3.1 | Independent security audit | 2027-07-19 | 2027-07-30
7.4.1 | Final compliance sign-off | 2027-11-22 | 2027-11-24
8.0 | Training and change management | 2027-04-01 | 2027-11-18
8.1.1 | Change impact and training needs | 2027-04-01 | 2027-04-14
8.2.1 | Develop training materials | 2027-04-15 | 2027-05-05
8.3.1 | Wave 1 staff training | 2027-07-09 | 2027-07-15
8.3.2 | Wave 2 staff training | 2027-09-08 | 2027-09-14
8.3.3 | Wave 3 staff training | 2027-11-12 | 2027-11-18
8.4.1 | Customer communications (Wave 3) | 2027-10-21 | 2027-11-04
9.0 | Decommission and closure | 2027-11-22 | 2028-01-28
9.1.1 | Stability period (to end of freeze) | 2027-11-22 | 2028-01-07
9.2.1 | Archive legacy data | 2028-01-10 | 2028-01-14
9.3.1 | Decommission on-premises servers | 2028-01-17 | 2028-01-21
9.4.1 | Final project report | 2028-01-24 | 2028-01-27
9.5.1 | Closure and sponsor sign-off | 2028-01-28 | 2028-01-28
M6 | Project closed | 2028-01-28 | 2028-01-28 | [51 empty] | ◆